## Sheet1
COURTWALA - 8 MEETING PLAN FYP 1
Sno# | Task | Meeting# | Start Date | End Date | Responsibility
1 | Present idea and get advisor approval | 1 |  | 2025-10-04 | All
2 | Functional Requirement Specifications | 2 | 2025-10-04 | 2025-10-18 | Hammad
| Database Tables/ERD |  |  |  | Moiz & Uzair
| Wireframes |  |  |  | Marium
3 | Develop user registration/login (Firebase authentication) | 3 | 2025-10-18 | 2025-11-01 | Marium, Moiz & Hammad
| Implement UI of Splash screen and Login/signup pages |  |  |  | Uzair
4 | Design and develop UI for player, court owner, and admin panels (Frontend) | 4 | 2025-11-01 | 2025-11-15 | Uzair & Hammad
| Start working on AI chatbot |  |  |  | Marium & Moiz
5 | Implement booking, approval, and management APIs (Backend) | 5 | 2025-11-15 | 2025-11-29 | Hammad, Moiz & Uzair
| Prompt Engineering |  |  |  | Marium
6 | Connect APIs to MySQL, ensure data flow between all modules | 6 | 2025-11-29 | 2025-12-13 | Marium, Hammad & Moiz
| AI Chatbot UI |  |  |  | Uzair
7 | Add matchmaking, location maps, and any other AI implementation left | 7 | 2025-12-13 | 2025-12-27 | All
8 | Final integration, testing, and evaluation preparation | 8 | 2025-12-27 | 2025-01-10 | All
COURTWALA - 8 MEETING PLAN FYP 2
Sno# | Task | Meeting# | Start Date | End Date | Responsibility
1 | Review FYP 1 Internal Evaluation and FYP 2 Project Plan | 1 |  | 2026-02-28 | All
2 | Fix validation issue all over the app , Multiple slot selection fix | 2 | 2028-02-26 | 2026-03-14 | Validations fix: Moiz, Slot Selection fix: Marium
| 20% Advance Payment Model Implementation |  |  |  | Marium
3 | Backend Implementation of Advanced Matchmaking Feature | 3 | 2026-03-14 | 2026-03-28 | Marium and Moiz
4 | Remaining Backend Implementation and UI screens of Matchmaking | 4 | 2026-03-28 | 2026-04-11 | Backend: Marium, UI screens: Uzair
| Report Update |  |  |  | Report: Hammad
5 | Backend Implementation of Community Feed | 5 | 2026-04-11 | 2016-04-25 | Marium and Moiz
6 | Remaining Backend Implementation and UI screens of Community Feed | 6 | 2026-04-25 | 2026-05-09 | Backend: Marium, UI screens: Uzair
| Report Update |  |  |  | Report: Hammad
7 | Testing and Final checks, (might add an extra feature for shop sports items) | 7 | 2026-05-09 | 2026-05-23 | All
8 | Final testing, evaluation preparation and Report | 8 | 2026-05-23 | 2026-06-06 | Testing: Marium, Evalutaion: Uzair & Moiz, Report: Hammad